AI Security Posture Management

Platform

Complete Project Plan  ·  8-Week Accelerated MVP

| Document type | Full project plan — architecture, delivery, testing, risks, sign-off |
| --- | --- |
| Project | AI-SPM Enterprise Security Platform — MVP Build |
| Duration | 8 weeks suggested — estimated 12-week baseline |
| Client reviews | 3 structured checkpoints — end of Weeks 3, 6, and 8 |
| Deployment | Docker Compose (MVP) · Kubernetes post-launch roadmap |
| Version | v2.0 · June 2025 · Enhanced edition |

CLASSIFICATION: CONFIDENTIAL — CLIENT RESTRICTED

# Table of Contents

1.  Problem Statement & Business Case

2.  Solution Overview — What AI-SPM Does

3.  System Architecture — The Four Layers

4.  Technology Stack

5.  8-Week Project Plan

6.  Client Review Checkpoints

7.  Scope Definition

8. Approval and Sign-off

# 1.  Problem Statement & Business Case

Modern organisations increasingly rely on AI tools — ChatGPT, Claude, Gemini, AWS Bedrock — to accelerate work across every department. HR summarises CVs, finance models projections, developers write code, legal drafts contracts. The productivity gains are real and significant.

But a critical security gap has opened alongside that productivity. When employees connect directly to external AI services, there is no checkpoint, no inspection, and no audit trail. Sensitive company data crosses organisational boundaries with no visibility and no control.

## 1.1  The Core Risk

The risk is not hypothetical — it is happening now, in every organisation that allows direct AI tool access:

- A finance analyst pastes the full payroll dataset into ChatGPT to ask it to "find anomalies"

- A developer copies an internal API key and database schema into Gemini while debugging

- An HR manager sends a candidate's full identity details — CNIC, address, bank account — to Claude for summarisation

- A sales executive uploads an NDA-protected client contract to extract key dates

- A malicious insider uses AI to exfiltrate confidential pricing strategies disguised as "formatting help"

In every case, sensitive data has left the organisation permanently. There is no recall, no notification, and no audit trail. The organisation does not know it happened.

## 1.2  The Business Case

| Without AI-SPM | With AI-SPM |
| --- | --- |
| No visibility into what data employees share with AI | Complete audit trail of every AI interaction |
| No way to enforce policies — HR sees finance data, devs see customer records | Role-based access controls enforced automatically on every request |
| PII and trade secrets sent to third-party AI in plaintext | All sensitive data masked before leaving the network |
| No defence against prompt injection attacks on AI systems | Real-time threat detection and blocking |
| Cannot demonstrate compliance to regulators | Full audit logs ready for GDPR, ISO 42001, SBP reporting |
| Productivity blocked by blanket AI bans (blunt instrument) | Productivity enabled safely — employees use AI, security is silent |

# 2.  Solution Overview — What AI-SPM Does

AI-SPM is an enterprise security gateway that sits transparently between employees and external AI models. The employee experience is unchanged — they continue using their preferred AI tool — but every prompt is intercepted, inspected, and sanitised before reaching the AI, and every response is checked before being returned.

Think of it like a security checkpoint at an airport. Nothing gets through without being inspected

## 2.1  The Fundamental Mechanism

The platform intercepts traffic at the network level using a reverse proxy (Kong or Envoy). This means employees do not need to install anything or change their workflow. The gateway URL replaces the direct AI API endpoint in company tools and configurations.

Once a prompt arrives at the gateway, it passes through a sequential pipeline before the AI ever sees it:

- Authentication — verify the user's identity and role

- PII scanning — detect and mask all sensitive data

- Policy check — verify this user is allowed to do this action

- Threat detection — check for injection attacks and jailbreak attempts

- Forwarding — send the clean, masked prompt to the selected AI model

- Response inspection — check the AI's reply before returning it

- Audit logging — record the full interaction with all metadata

## 2.2  What It Protects Against

The platform addresses four distinct categories of risk:

Data exfiltration prevention

• Personal data (names, CNICs, emails, phone numbers, credit card numbers, SSNs) is automatically masked • Custom company-specific patterns (internal project codenames, account numbers, API keys) are detected and masked • The masked data never reaches the external AI — it is replaced with tokens before the request leaves the network

Compliance and audit

• Every interaction is logged with user identity, timestamp, detected entities, policy decisions, and threat scores • Logs are immutable and queryable — compliance teams can demonstrate exactly what happened in any incident • Reports can be generated for GDPR Article 30 (records of processing), ISO 42001 audits, and regulatory inspections

# 3.  System Architecture — The Four Layers

The platform is built as four distinct layers, each with a single clear responsibility. This separation means each layer can be upgraded, scaled, or replaced independently without affecting the others.

| Layer | Name | Core responsibility | Technologies |
| --- | --- | --- | --- |
| 1 | Agent + Gateway | Agent + Gateway dual-component design for complete AI traffic control | Kong / Envoy, JWT, TLS |
| 2 | Security Layer | The brain of the system. Runs PII detection and masking, enforces policy rules, scans for AI-specific threats, and decides whether to allow, modify, or block the request. | Presidio, spaCy, Garak, Guardrails AI |
| 3 | Storage Layer | Persists everything — audit logs, request metrics, policy configurations, user roles, and security events. The source of truth for compliance reporting. | PostgreSQL, structured JSON logging |
| 4 | Dashboard Layer | Gives security teams full visibility. Request volumes, blocked events, security scores, policy builder, user management, and exportable audit logs. | React, TypeScript, Tailwind CSS |

## 3.1  Security Mechanisms

The PII engine is built on Microsoft Presidio, augmented with spaCy's named entity recognition models. It operates in two passes: a pattern-matching pass for structured data types (credit card numbers, CNICs, SSNs follow predictable formats), and a contextual NLP pass for unstructured data (names, organisations, locations that only make sense in context).

| Entity type | Detection method | Example (original → masked) |
| --- | --- | --- |
| Full name | NLP contextual detection | Ahmed Khan → [MASKED-NAME-001] |
| CNIC number | Regex pattern 5-7-1 format | 35202-1234567-9 → [MASKED-CNIC-001] |
| Credit card | Luhn-validated pattern | 4111 1111 1111 1111 → [MASKED-CC-001] |
| Email address | RFC 5322 pattern | ahmed@company.com → [MASKED-EMAIL-001] |
| Phone number | International format patterns | +92-300-1234567 → [MASKED-PHONE-001] |
| Bank account | Pattern + context | PK36SCBL0000001123456702 → [MASKED-IBAN-001] |
| Company secrets | Custom rule engine | Project Falcon pricing → [MASKED-CUSTOM-001] |

The masking is token-preserving — the same piece of PII gets the same token within a session, so the AI can still answer coherently ("tell me about [MASKED-NAME-001]'s performance" still works correctly). The mapping between real data and tokens is stored only in the Storage Layer and never sent to the AI.

## 3.2  Policy Engine

Policies are defined as structured rules that attach to user roles. The policy engine evaluates rules in priority order and takes the first matching action. Administrators define rules through the visual policy builder in the dashboard — no code required.

Example policies from the default rule set:

- HR role + any AI model: ALLOW — with PII masking enabled, payroll file upload BLOCKED

# 4.  Technology Stack

Every technology in this stack was selected for three criteria: production-grade maturity, active maintenance, and suitability for the 8-week timeline. No experimental libraries. No vendor lock-in for core functionality.

| Category | Technology | Why chosen | Alternative considered |
| --- | --- | --- | --- |
| Gateway | Kong / Envoy | Mature, plugin-rich, handles 10k+ req/s | NGINX (less AI-aware plugin ecosystem) |
| Backend | FastAPI (Python) | Async, type-safe, auto-generates OpenAPI docs | NestJS — equally valid; decide at kickoff |
| Frontend | React + TypeScript | Ecosystem depth, team familiarity, component reuse | Vue 3 — viable but smaller team expertise |
| Styling | Tailwind CSS | Fastest path to professional UI without custom CSS debt | Material UI — heavier, less flexible |
| Database | PostgreSQL | ACID compliance, JSON support, battle-tested for audit logs | MySQL — less powerful JSON querying |
| PII detection | Microsoft Presidio | Purpose-built for PII, customisable, multilingual support | AWS Comprehend — cloud-only, vendor lock-in |
| NLP models | spaCy | Fast, production-ready NER, supports custom models | HuggingFace — more powerful but slower |
| AI security | Garak + 0DIN | Only dedicated AI security testing frameworks available | Custom rules only — insufficient coverage |
| Guardrails | Guardrails AI | Policy-as-code for LLM outputs, integrates with Presidio | Custom implementation — weeks of work |
| CI/CD | GitHub Actions | Native GitHub integration, free for public repos, mature | Jenkins — more setup overhead |
| Deployment | Docker Compose | Reproducible, portable, minimal ops overhead for MVP | Kubernetes — planned post-MVP |

# 5.  8-Week Project Plan

The 8-week plan compresses the original 12-week baseline by running phases in parallel rather than sequentially. The key insight is that the dashboard and policy engine do not need to wait for PII detection to be complete — they can be scaffolded as soon as the gateway is stable.

Critical dependency: the gateway must be stable and reviewed by the client at the end of Week 3 before PII work can be finalised. The API contract agreed at Review 1 is the interface all subsequent layers depend on.

## Phase 1 — AI Gateway & Proxy  (Weeks 1–3)

| Phase 1 — AI Gateway & Proxy · Weeks 1–3 |  |
| --- | --- |
| Deliverables | Automated tests built alongside |
| • Request interception layer (Kong or Envoy configured as reverse proxy) • FastAPI base service with middleware, CORS, error handling • JWT authentication and session management • OpenAI GPT-4 and GPT-3.5 adapters • Anthropic Claude Sonnet/Opus adapter • Google Gemini adapter (stub — full in Phase 2) • Structured request and response logging • Rate limiting (token bucket per user and per organisation) • Health check and readiness endpoints (/health, /ready) • OpenAPI documentation auto-generated | • pytest: all route handlers, HTTP method coverage • pytest: JWT token validation (valid, expired, malformed, missing) • pytest: rate limiter — burst, sustained, per-user, per-org • Integration: Gateway → OpenAI mock end-to-end • Integration: Gateway → Claude mock end-to-end • Smoke: Health check endpoints always return 200 • Response schema validation (required fields present) • CI pipeline: GitHub Actions on every PR • Coverage gate: 80% minimum — PRs fail below threshold • CLIENT REVIEW 1 — End of Week 3: live demo + API contract sign-off |

## Phase 2 — PII Detection & Masking  (Weeks 3–6)

| Phase 2 — PII Detection & Masking · Weeks 3–6 |  |
| --- | --- |
| Deliverables | Automated tests built alongside |
| • Microsoft Presidio integration with spaCy en_core_web_lg model • Standard entity detection: names, emails, phones, credit cards, SSN • Pakistan-specific: CNIC 5-7-1 pattern with Luhn-style validation • IBAN and bank account detection (Pakistani and international formats) • Custom entity rule engine for company-specific secrets • Token-preserving masking engine (consistent tokens within session) • Masked prompt forwarding pipeline to LLM adapters • Response inspection — scan AI output before returning to user • PII detection event audit trail with entity types and confidence scores • Masking configuration UI (which entity types to mask, confidence threshold) | • PII accuracy benchmarks: precision and recall against labelled dataset • False positive rate tests (legitimate text must not be masked) • CNIC detection: valid and invalid format coverage • Credit card: Luhn validation + format variations • Masking correctness: token assignment consistency across sessions • End-to-end pipeline: raw prompt in, masked prompt to LLM, response back • Audit log integrity: every PII event written with correct metadata • Custom entity rule evaluation tests • Response inspection: injected PII in LLM response is caught and masked • CLIENT REVIEW 2 — End of Week 6: PII demo + scope freeze |

## Phase 3 — Policy Engine & Dashboard  (Weeks 5–8)

| Phase 3 — Policy Engine & Dashboard · Weeks 5–8 |  |
| --- | --- |
| Deliverables | Automated tests built alongside |
| • Policy rule engine: structured rule schema with priority ordering • Default RBAC roles: HR, Finance, Developers (fully configurable) • Model restriction rules: which roles can use which AI models • Topic blocking rules: keyword and semantic pattern matching • File upload restriction rules (block payroll, customer data, contracts) • Policy violation logging with context and user identity • Alert system: real-time notifications for high-severity violations • React + Tailwind admin dashboard with authentication • Request metrics dashboard: volumes, blocked %, trends • Visual policy rule builder: create rules without writing code • User management: assign roles, view usage, suspend access • Audit log viewer: filterable, searchable, CSV/JSON export • Security score display: organisation-wide and per-department | • Policy boundary tests: every rule combination for HR, Finance, Dev • RBAC permission matrix: 6×6 role/action coverage • Blocked prompt assertions: 50 blocked prompt scenarios • Policy violation logging: event written with correct metadata • Alert trigger tests: high-severity events fire notifications • React component unit tests (Jest + React Testing Library) • Dashboard: metrics displayed correctly for mock data sets • Policy builder: rule creation, editing, deletion flows • User management: role assignment, suspension, reinstatement • Audit log: filter, search, export CSV and JSON • Playwright E2E: full user journeys (login → use → audit → export) • Playwright E2E: policy create → apply → verify blocking |

## Phase 4 — Threat Detection & Launch  (Weeks 7–8)

| Phase 4 — Threat Detection & Launch · Weeks 7–8 |  |
| --- | --- |
| Deliverables | Automated tests built alongside |
| • Prompt injection detection (signature-based + Garak integration) • Jailbreak pattern matching (DAN, roleplay, token manipulation signatures) • Data extraction attack detection • Policy bypass detection (indirect circumvention attempts) • Threat score model (0–100, configurable block threshold) • Security score calculation model (org-wide and per-department) • Real-time alert system for critical threats • Docker Compose multi-service deployment configuration • Environment configuration (.env template, secrets management guide) • Load and performance testing (target: <200ms P95 for gateway) • Technical documentation (API reference, deployment guide, runbook) • Final test coverage report — target 80% across all services • CLIENT REVIEW 3 — End of Week 8: full demo, handover, go/no-go | • Garak attack suite: 100+ prompt injection patterns tested • Jailbreak regression suite: all known jailbreak signatures • Data extraction detection: 30 extraction pattern scenarios • Threat score calibration: score accuracy against labelled dataset • Auth bypass fuzzing: header manipulation, token forgery, session attacks • Locust load tests: gateway throughput at 100, 500, 1000 concurrent users • P95 latency gate: fail if gateway adds >200ms • Docker smoke test: full stack starts, health checks pass, end-to-end works • Documentation review: API reference completeness check • Final coverage report: all services ≥80% line coverage |

# 6.  Client Review Checkpoints

Each review is a structured session, not an informal demo. Each review ends with a documented sign-off or a documented list of blocking issues.

Reviews are scope freeze points: the client can raise change requests at any review, but changes are only incorporated after the next freeze point.

No scope changes are accepted during an active sprint.

## Review 1 — End of Week 3

Review 1 agenda

• Live demo of gateway proxy intercepting a real prompt • Authentication flow walkthrough — login, token generation, role resolution • OpenAI GPT-4 integration live test with a sample prompt • Anthropic Claude integration live test • CI pipeline demonstration — show a PR being tested and approved • API contract document reviewed and signed — this is the interface all subsequent phases depend on • Scope confirmation for Phase 2: custom PII entity list finalised • Risk review: any blockers from Week 1–3 discussed and resolved

Sign-off required: API contract document. Client signature on this document authorises Phase 2 to begin.

## Review 2 — End of Week 6

Review 2 agenda

• PII masking live demo — paste a document with CNIC, email, credit card — watch it mask • Custom entity detection demo — show company-specific secrets being masked • Policy rule builder walkthrough — create a rule that blocks Finance from uploading payroll files • Dashboard UI preview — metrics, user management, audit log • Test report presented: PII accuracy metrics, false positive rate, coverage percentage • SCOPE FREEZE: no new features accepted after this meeting • Written approval required before the final sprint begins

Sign-off required: scope freeze document. Any change requests submitted after this meeting are queued for post-MVP roadmap.

## Review 3 — End of Week 8  (Production Go/No-Go)

Review 3 agenda

• Full end-to-end system demonstration: employee submits prompt → gateway intercepts → PII masked → policy checked → AI responds → response inspected → audit logged • Security demonstration: attempt a prompt injection attack — show it being blocked • Test report: final coverage figure, security test results, load test results • Dashboard tour: metrics, audit logs, security score, policy management • Docker deployment: demonstrate starting the full stack from docker-compose up • Documentation handover: API reference, deployment guide, runbook, admin manual • Production go/no-go decision: formal approval to deploy or list of blockers

Sign-off required: production deployment authorisation. This document confirms the client accepts the system for production use and takes responsibility for their deployment configuration.

# 7.  Scope Definition

## 7.1  Included in the 8-Week MVP

| Feature | Description |
| --- | --- |
| AI gateway and proxy | Reverse proxy intercepts all AI requests; routes through security pipeline before forwarding to LLM |
| Multi-provider support | OpenAI GPT-4/3.5, Anthropic Claude, Google Gemini, AWS Bedrock — all through one unified gateway |
| JWT authentication | User identity and role resolved on every request; no request proceeds without valid authentication |
| PII detection and masking | Presidio + spaCy detecting 10+ entity types; token-preserving masking; custom rule support |
| Policy engine | Structured rule system with priority ordering; RBAC for HR, Finance, Developers |
| Threat detection | Prompt injection, jailbreak, and data extraction detection; configurable threat score threshold |
| Admin dashboard | React + Tailwind; metrics, policy builder, user management, audit log viewer |
| Audit logging | Every interaction logged with full metadata; immutable, queryable, exportable |
| Automated CI/CD | GitHub Actions; 80% coverage gate; Docker build + smoke test on every merge |
| Docker deployment | Full docker-compose configuration; .env template; secrets management guide |
| 3 client reviews | Structured sessions at Weeks 3, 6, 8 with written reports and formal sign-off |
| Technical documentation | API reference, deployment guide, operator runbook, admin manual |

## 7.2  Deferred to Post-MVP

| Feature | Why deferred | Planned phase |
| --- | --- | --- |
| Apache Kafka / Flink | Adds 3–4 weeks of infrastructure setup; not needed until processing >1M requests/day | Post-MVP Phase 5 |
| Neo4j graph database | Required for advanced relationship analytics; standard audit logs sufficient for MVP | Post-MVP Phase 5 |
| High-availability Kubernetes | Docker Compose handles MVP scale; K8s migration requires separate DevOps workstream | Post-MVP Phase 6 |
| Advanced Garak automation | Manual Garak runs sufficient for MVP; automated campaigns require additional tooling | Post-MVP Phase 5 |
| GDPR formal certification | Platform is compliance-ready; formal audit is a separate legal/compliance workstream | Post-MVP Phase 6 |
| ISO 42001 certification | Requires documented management system beyond the platform itself | Post-MVP Phase 6 |
| Multi-tenancy | Single-organisation MVP; multi-tenant architecture requires significant gateway changes | Post-MVP Phase 7 |

# Approval and Sign-off

By signing below, the authorised representatives confirm they have read, understood, and approved this project plan in full — including the scope definition, 8-week suggested (12 weeks estimated ) timeline.

| Client Representative Signature: _________________________________ Full name: __________________________________ Title: ________________________________________ Organisation: ______________________________ Date: _________________________________________ | Project Manager Signature: _________________________________ Full name: __________________________________ Title: ________________________________________ Organisation: ______________________________ Date: _________________________________________ |
| --- | --- |

| Technical Lead Signature: _________________________________ Full name: __________________________________ Date: _________________________________________ | Security Lead Signature: _________________________________ Full name: __________________________________ Date: _________________________________________ |
| --- | --- |

This document is version-controlled. Any amendments must be issued as a new version with change notes. The version in force at each review session is the definitive scope agreement for that phase.